## Risk register
No. | Risk | Description | Category | Root Cause | Avoidance plan | Contingency plan | Fall back plan
R1 | Member uncooperating | The member uncooperating with each others | People risk | Conflict between team member | Team building to connect member with each others. | Finding root conflict (social relationship, private conflict) | Trade-off strategy
R2 | Device problems | Different devices can not run like the devices was tested. | Technology | Different android devices with differents android's version and differrents manufactures. | Testing in as many as devices we can test and using settings to cover this issue. | Add new setting to cover the risk | Change algorithm.
R3 | Team member do not have enough appropriate skill, experience | Team member do not have enough appropriate skill, experience | People risk | All member are students | when developing project plan, estimate more time for study new technique | invite expertise to share experience and trainning | Overtime for complete task and gain experience
R4 | Changing in the way of executing | Team members find out the other ways to executing the project, reduce time and cost, such as better algorithm, technology. | Project team & Structure | Creative members |  | Meeting for evaluating, and changing the way to execute the project if it's really better | re-evaluate and consider the effective of changing the way of executing
R5 | Over deadline | Some members of team do not finish their tasks in time. | Technology & People | Low responsibility in working of members | Estimate time to plan task appropriate with ability of team members and hold daily meeting to keep track on project status day by day. | Other team members will support to help the task can complete in time | Overtime for complete task
R6 | Low quality infrastructure of the internet | The internet infrastructure is corrupted or damaged while project is executed, makes incident while project team is working and slows the durations of the project | Technology | Incident |  | Use other internet like 3G. | Repairing and upgrading (if necessary) the infrastructure
R7 | Conflict with other modules | Conflict with other modules in the system of customer. | Technology | Customer hire different company to do different modul in their system. | Contact with customer soon, review design together. | Rework conflict component. | Rework all module.